## ProjectTeam
Name | GitHub Alias
Marwin Philips | MarwinPhilips
Mete Turna | turnm1
Amin Ghodrati | ghodm1
Jonas Mosimann | QuanTumli
Michel Murbach | murbm1
Carole Kaiser | kaisc3

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Login | Anna can login, logout, change the password and register. |  | 20
3 | Medikamentenübersicht betrachten | Anna sees all her medicaments in an overwview |  | 20
4 | Medikamente erfassen | Anna adds a new medicament to her medication list. |  | 50
5 | Medikament editieren | Anna edits an existing medicament of her medication list |  | 40
6 | Medikament absetzen | Anna stops an existing medicament of her medication list |  | 10
7 | Medikament einnehmen | Anna applied her medicament. |  | 20
8 | Erinnerung an Medikament | Anna gets alarmed to take her medicament |  | 20
9 | Medikamente richten | Anna prepares her medicament for the Week |  | 15
11 | Medikamenteninformationen aufrufen | Anna wants to get more information about a medicament |  | 10
12 | Reservemedikament erfassen | Anna adds a new reserve medicament to her medication list |  | 10
13 | Medikamentenänderungen verfolgen | Anna tracks her medication changes. |  | 30

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 2 | Patient Model | Data model for patient record needs to be created based on standard.... | Database | Martin | Hans | medium | 2 | 2 | 0 | waiting
1.2 | 2 |  |  | UI, Controller | Hans | Jennifer | high | 8 | 6 | 4 | work in progress
1.3 | 1 |  |  | All | Martin | Tom | high | 16 | 20 | 20 | done
2.1 | 1 |  |  | Database | Tom | Martin | low | 4 | 10 | 4 | cancelled
2.2 | 2 |  |  | Main Window | Jennifer | Martin | high | 8 | 6 | 5 | work in progress

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180