## ProjectTeam
Name | GitHub Alias
Marwin Philips | MarwinPhilips
Mete Turna | turnm1
Amin Ghodrati | ghodm1
Jonas Mosimann | QuanTumli
Michel Murbach | murbm1
Carole Kaiser | kaisc3

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Medikamentenübersicht betrachten | Anna sees all her medicaments in an overwview |  | 36
2 | Medikamente erfassen | Anna adds a new medicament to her medication list. |  | 50
3 | Medikament editieren | Anna edits an existing medicament of her medication list |  | 40
4 | Medikament absetzen | Anna stops an existing medicament of her medication list |  | 10
5 | Medikament einnehmen | Anna applied her medicament. |  | 20
6 | Erinnerung an Medikament | Anna gets alarmed to take her medicament |  | 20
7 | Medikamente richten | Anna prepares her medicament for the Week |  | 15
8 | Medikamenteninformationen aufrufen | Anna wants to get more information about a medicament |  | 10
9 | Reservemedikament erfassen | Anna adds a new reserve medicament to her medication list |  | 10
10 | Medikamentenänderungen verfolgen | Anna tracks her medication changes. |  | 30
11 | Login | Anna can login, logout, change the password and register. |  | 20

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Medication Data Model | Data model for medication records needs to be created based on our developed class diagram. Create some simple example data | Database, JPA Classes | Marwin | Mete |  | 12 |  | 12 | done
1.2 | 1 | Navigation | Create top Navigation and View Controller, which can be used on every page | UI, Controller | Michel | Jonas |  | 12 |  | 12 | done
1.3 | 1 | Medication overview | Implement the Design as planned | UI, Controller, Modell | Amin | Carole |  | 12 |  | 12 | done
2.1 | 2 | Medication entry View | Create the planned Views for the entry of a new Medicament | UI, Controller | Mete | Amin |  | 20 |  |  | work in progress
2.2 | 2 | Medication Data Model | Optimize the medication dose schema to enter a new Medicament | Modell, Database | Marwin | Michel |  | 10 |  |  | work in progress
2.3 | 2 | Medication validation | Validate and save an entered medicament | Controller, Modell | Jonas | Marwin |  | 15 |  |  | work in progress
2.4 | 2 | Navigation | Navigate to the new View and Back | UI, Controller | Carole | Jonas |  | 4 |  |  | work in progress
3.1 | 2 | Medication edit View | Create the planned Editing view to edit an existing medicament by using 2,3. Do not implement history yet. | UI, Controller | Amin | Mete |  | 10 |  |  | work in progress
3.2 | 2 | Navigation | Navigate to the new view over the Medicationoverview-List | UI, Controller | Carole | Jonas |  | 5 |  |  | work in progress
4.1 | 2 | Stop a Medication | Stop an existing Medication over the Medicationoverview-List | UI, Controller, Modell | Michel | Marwin |  | 10 |  |  | work in progress
1.4 | 2 | GUI Optimization | Create a nice SCSS file to beautify our GUI | UI | Carole | Amin |  | 10 |  |  | work in progress

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180