## ProjectTeam
Name | GitHub Alias
Marwin Philips | MarwinPhilips
Mete Turna | turnm1
Amin Ghodrati | ghodm1
Jonas Mosimann | QuanTumli
Michel Murbach | murbm1
Carole Kaiser | kaisc3

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Medikamentenübersicht betrachten | Anna sees all her medicaments in an overwview |  | 36 |  |  | OK
2 | Medikamente erfassen | Anna adds a new medicament to her medication list. |  | 50 |  |  | OK
3 | Medikament editieren | Anna edits an existing medicament of her medication list |  | 40 |  |  | OK
4 | Medikament absetzen | Anna stops an existing medicament of her medication list |  | 10 |  |  | OK
5 | Medikament einnehmen | Anna applied her medicament. |  | 20 |  |  | sprint 3
6 | Erinnerung an Medikament | Anna gets alarmed to take her medicament |  | 20 |  |  | sprint 3
7 | Medikamente richten | Anna prepares her medicament for the Week |  | 15 |  |  | not used
8 | Medikamenteninformationen aufrufen | Anna wants to get more information about a medicament |  | 10 |  |  | sprint 3
9 | Reservemedikament erfassen | Anna adds a new reserve medicament to her medication list |  | 10 |  |  | OK
10 | Medikamentenänderungen verfolgen | Anna tracks her medication changes. |  | 30 |  |  | sprint 3
11 | Login | Anna can login, logout, change the password and register. |  | 20 |  |  | sprint 3

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Medication Data Model | Data model for medication records needs to be created based on our developed class diagram. Create some simple example data | Database, JPA Classes | Marwin | Mete |  | 12 |  | 12 | done
1.2 | 1 | Navigation | Create top Navigation and View Controller, which can be used on every page | UI, Controller | Michel | Jonas |  | 12 |  | 12 | done
1.3 | 1 | Medication overview | Implement the Design as planned | UI, Controller, Modell | Amin | Carole |  | 12 |  | 12 | done
2.1 | 2 | Medication entry View | Create the planned Views for the entry of a new Medicament | UI, Controller | Mete | Amin |  | 20 |  | 23 | done
2.2 | 2 | Medication Data Model | Optimize the medication dose schema to enter a new Medicament | Modell, Database | Marwin | Michel |  | 10 |  | 16 | done
2.3 | 2 | Medication validation | Validate and save an entered medicament | Controller, Modell | Jonas | Marwin |  | 15 |  | 13 | work in progress
2.4 | 2 | Navigation | Navigate to the new View and Back | UI, Controller | Carole | Jonas |  | 4 |  | 1 | done
3.1 | 2 | Medication edit View | Create the planned Editing view to edit an existing medicament by using 2,3. Do not implement history yet. | UI, Controller | Amin | Mete |  | 10 |  | 9 | work in progress
3.2 | 2 | Navigation | Navigate to the new view over the Medicationoverview-List | UI, Controller | Carole | Jonas |  | 5 |  | 1 | done
4.1 | 2 | Stop a Medication | Stop an existing Medication over the Medicationoverview-List | UI, Controller, Modell | Michel | Marwin |  | 10 |  | 11 | work in progress
1.4 | 2 | GUI Optimization | Create a nice SCSS file to beautify our GUI | UI | Carole | Amin |  | 10 |  | 15 | done
2.3.1 | 3 | Medication validation | Validate and save an entered medicament | UI, Controller | Carole | Mete |  | 10 |  | 0 | work in progress
3.1.1 | 3 | Medication edit View | functionality of the save button | UI, Controller | Marwin | Jonas |  | 5 |  | 0 | work in progress
4.1.1 | 3 | Stop a Medication | functionality of the delet button (save) | UI, Controller, Modell | Marwin | Jonas |  | 5 |  | 0 | work in progress
6.1 | 3 | Junit Test's | Create for the logical classes unit test's for testing | Test | All | All |  | 15 |  | 0 | work in progress
6.2 | 3 | Clean the Code | Code cleaning, comments, review | UI, Controller, Modell, Database | All | All |  | 15 |  | 0 | work in progress
7.1 | 3 | Medication Feedback Model | Implement the functionality of Feedback View | UI, Controller, Modell |  |  |  | 20 |  | 0 | work in progress
7.2 | 3 | Medication Feedback View | Create a Feedback View | UI, Controller, Modell |  |  |  | 20 |  | 0 | work in progress

## Sprint Work Time
Sprint ID | Sprint | Name | Effort Plan Original | Effort Actual | Programmer: | Marwin | Jonas | Mete | Carole | Amin | Michel
2.3.1 | 3 | Medication validation | 10 | 0
3.1.1 | 3 | Medication edit View | 5 | 0
4.1.1 | 3 | Stop a Medication | 5 | 0
6.1 | 3 | Junit Test's | 15 | 0
6.2 | 3 | Clean the Code | 15 | 0
7.1 | 3 | Medication Feedback Model | 20 | 0
7.2 | 3 | Medication Feedback View | 20 | 0

## BurndownChart
Burndown chart
|  | Burned down |  | Balance |  | Weekly Completed |  |  | Grafik
Date | Week | Planned | Actual | Planned | Actual
0 | 0 | 0 | 0 | 261 | 261 | 0
KW 48 | 1 | 32.63 | 36 | 228.37 | 225 | 36 | Start | Sprint1
KW 49 | 2 | 32.63 | 25 | 195.74 | 200 | 25
KW 50 | 3 | 32.63 | 29 | 163.11 | 171 | 29 |  | Sprint2
KW 51 | 4 | 32.63 | 35 | 130.48 | 136 | 35
KW 52 | 5 | 0 | 0 | 130.48 | 136 | 0
KW 53 | 6 | 32.63 | 0 | 97.85 | 136 | 0
KW 01 | 7 | 32.63 | 0 | 65.22 | 136 | 0 |  | Sprint3
KW 02 | 8 | 32.63 | 0 | 32.59 | 136 | 0
KW 03 | 9 | 32.63 | 0 | -0.04 | 136 | 0 | Schluss Präsi